## Cover
ENGINEERING DIVISION
Quarterly Performance Report
Q2 2026 (Apr – Jun 2026)
with comparison to Q1 2026
Reporting period | Q2 2026 (1 Apr – 30 Jun 2026)
Comparison baseline | Q1 2026 (1 Jan – 31 Mar 2026)
Data sources | Engineering Job Scheduling; Skid MDR Register
Data cut-off | 16 June 2026
Report date | 22 June 2026
Prepared by | Engineering Division
Scope & Data Notes
1. Job-scheduling KPIs are derived from activity Start Date within each quarter.
2. Q2 2026 reflects activity through the 16 Jun 2026 data cut-off (partial quarter).
3. 'NOD' = planned turnaround in days (End Date − Start Date).
4. On-time = Actual Completion Date on or before the planned End Date.
5. Skid MDR document data is 2025-dated; its Q1/Q2 split is aligned to the
quarterly timeline for trend comparison (calendar year differs — see Skid sheet).

## Executive Summary
EXECUTIVE SUMMARY — Q2 2026 vs Q1 2026
Engineering Job Scheduling — core delivery KPIs
Activities Completed | Completion Rate | On-Time Delivery
104 | 89.7% | 92.0%
Q1: 147 (▼ -43.0) | Q1: 93.0% (▼ -3.4 pp) | Q1: 87.8% (▲ +4.2 pp)
Avg Turnaround (days) | Active Job Orders | Late Activities
2.23 | 37 | 8
Q1: 2.46 (▼ -0.2) | Q1: 42 (▼ -5.0) | Q1: 18 (▼ -10.0)
Key Takeaways
On-time delivery improved
On-time completion rose from 87.8% in Q1 to 92.0% in Q2, and late activities fell from 18 to 8.
Turnaround tightened
Average planned turnaround improved from 2.46 to 2.23 days per activity — faster scheduled cycle times.
Lower throughput (partial quarter)
Q2 shows 116 activities vs 158 in Q1. Q2 data ends 16 Jun, so the quarter is ~2/3 elapsed; full-quarter volume is expected to land near Q1 levels.
Completion rate slightly down
Completion rate eased from 93.0% to 89.7%, reflecting 5 in-progress and 7 open items still inside the active quarter.
Skid MDR backlog needs attention
The skid document register carries 117 pending documents across 40 jobs; Kareem Malik (51) and Ashif Mujthaba (28) hold the largest shares.

## KPI Comparison
KPI COMPARISON — Engineering Job Scheduling
KPI | Q1 2026 | Q2 2026 | Change | Interpretation | Metric | Q1 2026 | Q2 2026
Total activities scheduled | 158 | 116 | -42 | Q2 partial (cut-off 16 Jun) | Completion % | 93 | 89.7
Unique job orders worked | 42 | 37 | -5 | Active project breadth | On-Time % | 87.8 | 92
Activities completed | 147 | 104 | -43 | Delivered output
Completion rate | 93.0% | 89.7% | -3.4 pp | Share of scheduled work completed
In-progress activities | 2 | 5 | +3 | Work-in-progress at cut-off | Metric | Q1 2026 | Q2 2026
Open / not-started | 9 | 7 | -2 | Backlog inside quarter | Scheduled | 158 | 116
On-time deliveries | 129 | 92 | -37 | Completed on/before End Date | Completed | 147 | 104
Late deliveries | 18 | 8 | -10 | Completed after End Date | Late | 18 | 8
On-time delivery rate | 87.8% | 92.0% | +4.2 pp | Schedule reliability
Avg planned turnaround (days) | 2.46 | 2.23 | -0.22 | Lower = faster cycle time
Total planned engineering-days | 383 | 248 | -135 | Scheduled effort volume

## Activity Mix
ACTIVITY MIX — Top Engineering Activity Types
Count of scheduled activities by type (Q1 vs Q2 2026)
Activity Type | Q1 2026 | Q2 2026 | Total
GAD | 12 | 9 | 21
Concept Design and Feasibility Study | 9 | 4 | 13
DXF file creation for the Sheetmetal | 8 | 4 | 12
Fabrication Drawings | 7 | 5 | 12
Tags and Caution Sticker Drawing | 7 | 4 | 11
Testing Procedure | 6 | 5 | 11
Operation & Maintenance Manual | 5 | 4 | 9
Weight and CG Calculation | 3 | 6 | 9
BOQ | 3 | 5 | 8
Electrical Wiring Diagrams | 7 | 1 | 8
AS-BUILT DRAWING | 5 | 2 | 7
Work Instruction Creation | 4 | 2 | 6
SFD | 4 | 2 | 6
Assembly Drawings | 2 | 4 | 6
BOQ Release | 5 | 1 | 6

## Engineer Workload
ENGINEER WORKLOAD & PRODUCTIVITY
Activities scheduled per engineer (Q1 vs Q2 2026)
Engineer | Q1 2026 | Q2 2026 | Total | Share of Total
Sathish | 45 | 39 | 84 | 30.66%
Khursheed | 48 | 11 | 59 | 21.53%
Sijo | 18 | 29 | 47 | 17.15%
Vignesh | 18 | 17 | 35 | 12.77%
Sohail | 13 | 11 | 24 | 8.759%
Mazhar | 6 | 6 | 12 | 4.38%
Al Rafae | 7 | 1 | 8 | 2.92%
Mahin | 3 | 0 | 3 | 1.095%
(Unassigned) | 0 | 2 | 2 | 0.7299%
TOTAL | 158 | 116 | 274 | 100%

## Skid MDR Status
SKID PROJECTS — MDR DOCUMENT STATUS
Master Document Register submission tracking (Skid Pending Documents)
Note: source dates are in calendar year 2025; Q1/Q2 split shown for quarter-over-quarter trend. Totals reflect current register snapshot.
Total documents | Completed | Pending | Skid jobs
365 | 244 | 117 | 40
Skid MDR KPI | Q1 | Q2 | Change
Documents due (planned) | 193 | 119 | -74
Completed | 180 | 63 | -117
Pending | 13 | 56 | +43
Completion rate | 93.3% | 52.9% | -40.3 pp
On-time submission rate | 14.8% | 33.3% | +18.6 pp
Skid jobs touched | 29 | 29 | +0
Pending Document Backlog by Assignee
Assignee | Pending Docs
Kareem Malik | 51
Ashif Mujthaba | 28
Prem Kumar | 12
Pavan Kumar | 8
Mahin Basheer | 7
Raheem Shaikh | 4
Mohammed AlRefae | 4
Tijo Thilakan | 3
|  |  |  | Stage | Q1 | Q2
|  |  |  | Completed | 180 | 63
|  |  |  | Pending | 13 | 56

## Division KPIs
ENGINEERING DIVISION — COMBINED OUTPUT
Job-scheduling activities + skid MDR documents
Work Stream | Items Completed | Open / Pending | Quality
Job-scheduling activities (Q2 2026) | 104 | 12 | On-time 92.0%
Job-scheduling activities (Q1 2026) | 147 | 11 | On-time 87.8%
Skid MDR documents (register) | 244 | 117 | 66.8% complete
Recommendations / Focus for Q3 2026
1. Sustain the on-time gain: lock in the Q2 schedule-reliability improvement (87.8% → 92.0%) by holding planning discipline on turnaround.
2. Clear the skid MDR backlog: 117 pending documents are concentrated on two assignees — rebalance load and set weekly submission targets.
3. Close out in-quarter WIP: 5 in-progress and 7 open activities should be driven to completion before quarter close.
4. Validate full-quarter Q2 volume after 30 Jun: current figures are through 16 Jun and will rise.
5. Watch workload concentration: a few engineers carry the majority of scheduled activities — consider cross-loading to reduce single-point dependency.